## Summary
Metric | Actual result
Date | 2026-10-10
Branch | feat/uart-uvm-verification
Unique testcases | 29
DUT cases / checker self-test | 28 / 1
Regression runs | 33
PASS / FAIL / UNKNOWN | 23 / 10 / 0
RTL integrity | 9 files: SHA-256 identical to baseline 9ccfd39
RTL bug status | UART-001 OPEN; UART-002 OPEN; UART-003 OPEN
Merge policy | No merge; push feature branch only
Estimate | 5 engineering days: requirements 0.5; VIP/env 1.5; tests 2; debug/report 1
Coverage scope | Observed exercise coverage; failing tests do not prove specification compliance
1. Register | PASS=3 FAIL=0 UNKNOWN=0
2. AHB access | PASS=3 FAIL=0 UNKNOWN=0
3. Baud generator | PASS=2 FAIL=0 UNKNOWN=0
4. UART TX | PASS=1 FAIL=1 UNKNOWN=0
5. UART RX | PASS=2 FAIL=1 UNKNOWN=0
6. FIFO | PASS=3 FAIL=0 UNKNOWN=0
7. Interrupt | PASS=5 FAIL=0 UNKNOWN=0
8. Parity error | PASS=1 FAIL=3 UNKNOWN=0
9. Integration and checker | PASS=3 FAIL=1 UNKNOWN=0

## Vplan
Total Items | 29
Pass Items | 23
Fail Items | 6
NY Items | 0
Signoff | NOT CLOSED: three confirmed RTL defects; W1C set-to-clear coverage blocked by UART-002
Section | Main Title | Description | Testname | Priority | Method / Checker | Owner | Status | Milestone | Remark / Bug ID | Spec section | Seeds / Evidence
REG-01 | 1. Register | All defined reset values, idle TX, interrupt reset and reset after programmed state | uart_register_reset_test | P1 | Independent constants + register scoreboard; RBR undefined reset value excluded | DV | PASS | 2026-10-10 | Executed with independent checks | 2.2, Tables 2-3 to 2-10 | seed=1 PASS sim/log/uart_register_reset_test_1.log
REG-02 | 1. Register | Walking-one/zero across 32 bits, 100 random writes/reads, implemented masks, FSR RO bits and ignored RBR writes | uart_register_access_test | P1 | Register prediction and explicit expected values; compare all read data bits | DV | PASS | 2026-10-10 | Executed with independent checks | 2.1–2.2 | seed=1 PASS sim/log/uart_register_access_test_1.log
REG-03 | 1. Register | UVM RAL frontdoor reset/read/write/mirror over AHB | uart_regmodel_test | P1 | RAL mirror and independent register scoreboard | DV | PASS | 2026-10-10 | Executed with independent checks | 2.2 | seed=1 PASS sim/log/uart_regmodel_test_1.log
AHB-01 | 2. AHB access | 400 mixed SINGLE and one-beat INCR transfers with wait states | uart_ahb_transfer_test | P1 | Completed transfer count and independent write/read data checks | DV | PASS | 2026-10-10 | Executed with independent checks | 1.2, 1.6.1 | seed=1 PASS sim/log/uart_ahb_transfer_test_1.log
AHB-02 | 2. AHB access | IDLE, BUSY and unselected writes must have no side effect | uart_ahb_idle_test | P1 | Unchanged register value and zero extra completed transfers | DV | PASS | 2026-10-10 | Executed with independent checks | 1.6.1 | seed=1 PASS sim/log/uart_ahb_idle_test_1.log
AHB-03 | 2. AHB access | All 248 aligned reserved words, read and write, recovery after every error | uart_reserved_access_test | P1 | 496 HRESP errors, two-cycle ERROR protocol, FFFFFFFF read data, subsequent legal access | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7.3, 2.2 | seed=1 PASS sim/log/uart_reserved_access_test_1.log
BAUD-01 | 3. Baud generator | 26 settings: both oversampling modes, all 14 spec-table examples, divisors 1/2/255/256/257/65535 | uart_baud_test | P1 | Measure actual TX data-bit edge interval; end-to-end TX and RX at each setting | DV | PASS | 2026-10-10 | Executed with independent checks | 1.5 Tables 1-4, 1-5 | seed=1 PASS sim/log/uart_baud_test_1.log
BAUD-02 | 3. Baud generator | BGE=0 pauses transmission; enabling drains queued bytes | uart_baud_disable_test | P1 | Zero frames/idle output while disabled; compare both queued frames after enable | DV | PASS | 2026-10-10 | Executed with independent checks | 2.2.4 BGE | seed=1 PASS sim/log/uart_baud_disable_test_1.log
TX-01 | 4. UART TX | 48 frame configurations, each with 00/FF/55/AA: 192 frames | uart_tx_format_test | P1 | Pin decoder checks data width/order, data, parity, every stop-bit center | DV | FAIL | 2026-10-10 | UART-001 | 1.6.2.1, 2.2.4 | seed=1 FAIL sim/log/uart_tx_format_test_1.log
TX-02 | 4. UART TX | All 256 byte values at 8N1 | uart_tx_data_test | P1 | TBR-to-pin scoreboard, exact count, pending and unexpected frame guards | DV | PASS | 2026-10-10 | Executed with independent checks | 1.6.2.1, 1.7.1 | seed=1 PASS sim/log/uart_tx_data_test_1.log
RX-01 | 5. UART RX | 48 configurations with 00/FF/55/AA: 192 back-to-back frames | uart_rx_format_test | P1 | Monitor validates stimulus; independent data expected at RBR; valid parity leaves status clear | DV | PASS | 2026-10-10 | Executed with independent checks | 1.6.2.2, 2.2.4 | seed=1 PASS sim/log/uart_rx_format_test_1.log
RX-02 | 5. UART RX | All 256 byte values at 8N1 | uart_rx_data_test | P1 | Stimulus-to-monitor-to-RBR comparisons and exact receive count | DV | PASS | 2026-10-10 | Executed with independent checks | 1.6.2.2, 1.7.2 | seed=1 PASS sim/log/uart_rx_data_test_1.log
RX-03 | 5. UART RX | 5N1 at 13x/divisor 2: eight spaced frames as control, then eight back-to-back 0x17 frames | uart_rx_13x_div2_test | P1 | Pin stimulus decoder confirms 260 ns bits; RBR must return 0x17 for all 16 frames; off-clock-edge stimulus | DV | FAIL | 2026-10-10 | UART-003 | 1.5, 1.6.2.2 | seed=1 FAIL sim/log/uart_rx_13x_div2_test_1.log
FIFO-01 | 6. FIFO | Three paused TX fill/drain rounds; 16 FIFO entries + one prefetched byte; nine ignored full writes; wraparound | uart_tx_fifo_test | P1 | FSR boundaries, explicit rejected-write expectations, all 51 accepted bytes in order | DV | PASS | 2026-10-10 | Executed with independent checks | 1.2, 1.7.1, 1.7.3 | seed=1 PASS sim/log/uart_tx_fifo_test_1.log
FIFO-02 | 6. FIFO | Fill TX FIFO with BGE enabled and slow baud, reject three extra writes, drain | uart_tx_active_full_test | P1 | Independent acceptance/rejection list, FSR full/empty, 17 exact frame comparisons | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7.3 | seed=1 PASS sim/log/uart_tx_active_full_test_1.log
FIFO-03 | 6. FIFO | Three fill/drain rounds of exactly 16 RX bytes; FIFO pointer wraparound | uart_rx_fifo_test | P1 | FSR after each receive, ordered 48 RBR comparisons, final empty | DV | PASS | 2026-10-10 | Executed with independent checks | 1.2, 1.7.2 | seed=1 PASS sim/log/uart_rx_fifo_test_1.log
IRQ-01 | 7. Interrupt | All 32 enable masks at reset FIFO status 0xA | uart_irq_mask_test | P1 | IRQ equals OR of enabled active sources, checked from independent expected status | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7, 2.2.5 | seed=1 PASS sim/log/uart_irq_mask_test_1.log
IRQ-02 | 7. Interrupt | Assert TX empty, clear when queued nonempty, reassert after drain, mask | uart_irq_tx_empty_test | P1 | Pin-level IRQ checks and two transmitted bytes | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7.1, 2.2.5 | seed=1 PASS sim/log/uart_irq_tx_empty_test_1.log
IRQ-03 | 7. Interrupt | Assert TX full, deassert after FIFO drain | uart_irq_tx_full_test | P1 | Pin-level IRQ plus exact 17-byte transfer count | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7.1, 2.2.5 | seed=1 PASS sim/log/uart_irq_tx_full_test_1.log
IRQ-04 | 7. Interrupt | Assert RX empty, clear on receive, reassert on drain, mask | uart_irq_rx_empty_test | P1 | Pin-level IRQ and RBR comparison | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7.2, 2.2.5 | seed=1 PASS sim/log/uart_irq_rx_empty_test_1.log
IRQ-05 | 7. Interrupt | Assert on 16th received byte, clear on first RBR read | uart_irq_rx_full_test | P1 | IRQ levels and all 16 received bytes compared | DV | PASS | 2026-10-10 | Executed with independent checks | 1.7.2, 2.2.5 | seed=1 PASS sim/log/uart_irq_rx_full_test_1.log
PAR-01 | 8. Parity error | Bad parity across both modes, all widths, even/odd; sticky flag, write-zero, W1C, IRQ masking | uart_parity_error_test | P1 | Wire error injection independently monitored; FSR and IRQ explicit checks; W1C clearing blocked by missing set | DV | FAIL | 2026-10-10 | UART-002 | 2.2.4 PEN/EPS, 2.2.5 bit4, 2.2.6 bit4 | seed=1 FAIL sim/log/uart_parity_error_test_1.log
PAR-02 | 8. Parity error | PEN=0 ignores requested parity injection; 00 and FF data | uart_parity_disabled_test | P1 | No parity slot generated; no FSR error or parity IRQ; two RBR comparisons | DV | PASS | 2026-10-10 | Executed with independent checks | 2.2.4 PEN | seed=1 PASS sim/log/uart_parity_disabled_test_1.log
PAR-03 | 8. Parity error | Minimal 8E1 TX reproduction with bytes 00 and 01 | uart_tx_parity_bug_test | P1 | UVM serial parity checker and independent offline VCD decoder | DV | FAIL | 2026-10-10 | UART-001 | 1.6.2.1, 2.2.4 EPS | seed=1 FAIL sim/log/uart_tx_parity_bug_test_1.log
PAR-04 | 8. Parity error | Minimal 8E1 RX wrong-parity reproduction: 00 with parity=1 | uart_rx_parity_bug_test | P1 | Independent VCD proof of injected parity error; FSR/IRQ checks; no error demotion | DV | FAIL | 2026-10-10 | UART-002 | 2.2.4, 2.2.5, 2.2.6 | seed=1 FAIL sim/log/uart_rx_parity_bug_test_1.log
SYS-01 | 9. Integration and checker | Reset, initialization, two TX bytes and one RX byte | uart_smoke_test | P1 | Register, bidirectional scoreboard and exact counts | DV | PASS | 2026-10-10 | Executed with independent checks | Chapter 3 | seed=1 PASS sim/log/uart_smoke_test_1.log
SYS-02 | 9. Integration and checker | 24 random configurations x 8 simultaneous TX/RX frames per seed; five seeds | uart_duplex_random_test | P1 | Independent per-direction queues, all frame properties, final FSR/counts; reset before each configuration | DV | FAIL | 2026-10-10 | UART-001; UART-003 | 1.2, 1.6, Chapter 3 | seed=1 FAIL sim/log/uart_duplex_random_test_1.log; seed=2 FAIL sim/log/uart_duplex_random_test_2.log; seed=3 FAIL sim/log/uart_duplex_random_test_3.log; seed=4 FAIL sim/log/uart_duplex_random_test_4.log; seed=5 FAIL sim/log/uart_duplex_random_test_5.log
SYS-03 | 9. Integration and checker | Reset during TX, reset during RX, recovery and subsequent transfers | uart_reset_traffic_test | P1 | Abort old frames/expectations; reset register/status checks; new frames compared | DV | PASS | 2026-10-10 | Executed with independent checks | 2.2 defaults, verification robustness | seed=1 PASS sim/log/uart_reset_traffic_test_1.log
SYS-04 | 9. Integration and checker | Checker self-test: incomplete trailing TX and RX frame must prevent silent pass | uart_monitor_tail_test | P1 | Isolated synthetic loopback, exactly one caught monitor error per direction; no DUT error catchers | DV | PASS | 2026-10-10 | Checker self-test; isolated pins, not a DUT compliance result | UVM GUIDE 7–8, 15 | seed=1 PASS sim/log/uart_monitor_tail_test_1.log

## Bugs
Bug ID | State | Severity | Required behavior | Observed behavior | Reproduction | Localization / limit
UART-001 | OPEN | High | Spec 1.6.2.1 / 2.2.4: in 8E1, parity(0x00)=0 and parity(0x01)=1; total ones including parity is even. | Pin decoder observes parity(0x00)=1 and parity(0x01)=0. Stop bits and payload are correct. TX format matrix and randomized duplex also fail parity checks. | make -C sim build COV=ON; make -C sim run TESTNAME=uart_tx_parity_bug_test SEED=1 COV=ON (expected nonzero) | Transmitter parity generation path. LCR=0x3B is read back correctly. Independent VCD decoder confirms wrong parity on uart_txd. uart_transmiter.vp is encrypted; exact internal expression cannot be identified. RTL unchanged.
UART-002 | OPEN | High | Spec 2.2.4/2.2.5/2.2.6: wrong RX parity with PEN=1 must set FSR[4], assert interrupt when IER[4]=1, remain sticky until W1C. | Valid 8E1 data 0x00 with injected parity=1 is received as 0x00, but FSR=0x0A (bit4=0) and interrupt=0. Full error matrix reproduces missing status for both sampling modes, all widths and even/odd parity. Set-to-clear W1C behavior remains blocked, not proven passing. | make -C sim build COV=ON; make -C sim run TESTNAME=uart_rx_parity_bug_test SEED=1 COV=ON (expected nonzero) | Receiver parity-error reporting path: readable top-level s_parrity_error never asserts in the minimal waveform. PEN/EPS/LCR and error stimulus are verified. uart_receiver.vp and apb_decoder.vp bodies are encrypted; do not claim an exact internal source line. RTL unchanged.
UART-003 | OPEN | High | Spec 1.5/1.6.2.2: at 13x divisor 2, valid 5N1 back-to-back frames have 260 ns bits and 1820 ns frame spacing; each 0x17 must be received intact. | Eight back-to-back 0x17 frames produce seven 0x17 bytes then 0x1B. An otherwise identical stream with one extra idle bit is correct. The error persists with RX edges shifted 1 ns away from HCLK. | make -C sim run TESTNAME=uart_rx_13x_div2_test SEED=1 COV=ON (expected nonzero). Also observed in duplex seeds 2–5. | Receiver frame timing path: read-only rx_wr pulses in the minimal contiguous stream are 1840 ns apart despite 1820 ns input frame spacing. Independent VCD decoder verifies the input. Protected receiver body prevents exact source-line diagnosis. RTL unchanged.

## Coverage
Coverage item | Measured result | Evidence / limitation
Functional aggregate | 97.50% | Four covergroups; results/functional_coverage.txt. Includes completed failing runs, not compliance.
Functional bins | 449 / 450 (99.77% tool display) | Only missing bin: FSR parity_error=1; blocked by UART-002.
Bus group | 100% | 33/33 bins; register/direction cross 18/18; reserved errors; SINGLE and one-beat INCR.
Frame group | 100% | 96/96 format cross bins, 256/256 payload bins; exercise coverage includes failing frames.
Status group | 90% | FSR parity_error=1 never observed; other FSR states hit.
IRQ group | 100% | All 32 masks and both levels observed. Parity IRQ assertion remains blocked by UART-002.
Available DUT statements | 1 / 1 (100%) | Only exposed instrumented statement; protected implementation bodies are not covered as source.
Available DUT expressions | 4 / 5 (80%) | Top-level IRQ expression; parity-error contribution missing.
Available DUT toggles | 550 / 596 (92.28%) | Readable hierarchy signals/ports; see results/dut_code_coverage.txt.
Available DUT code aggregate | 90.76% | Filtered /tb/dut recursive report; NOT full internal RTL code coverage.
Parity W1C and sticky behavior | BLOCKED | UART-002 prevents initial set. Returning zero after W1C is insufficient proof.
Live divisor reconfiguration | NOT CLAIMED | Independent configurations reset per Chapter 3; live switch timing unspecified.
Coverage merge inputs | 33 completed runs | Exact final manifest; stale UCDB files excluded; results/coverage_inputs.txt.